## Sheet1
ORG | CONCEPTUAL ELEMENTS | POSITION/DESCRIPTION | STATUS (%/complete/unknown) | CHALLENGE | NEXT STEP FOR NAVIGATORS | NEXT STEP FOR ORG | STRONG/ ADEQUATE/ WEAK
Example organization A
| HOOK | One sentence description of the development project, using simple language. "How you explain this to someone?" | Complete |  |  |  | Strong | Very strong hook which speaks to
| PROJECT CHARTER | Formal document which defined the scope, deliverables and goal of the project. | 75% |  | Navigators to support | Organization to work on / refine internally | Adequate
| PROGRAM LIST | Listing the elements which are going to be in the new project | Complete |  |  |  | strong | fleshed out and reviewed with organization!
| BUSINESS FEASIBILITY | The hypothetical business case of the project. High-level assessment revenue vs expenses. | 50% |  |  | Organization having internal conversations | Adequate
| ZONING ENVELOPE | Created zoning envelope. | Complete |  |  |  | strong | Very clear
| ZONING ENVELOPE (REFINED) | Adjusted created zoning envelope. | Complete |  |  |  | strong | Refined are nicely detailed
| CONCEPT DESIGN (INTENTION) | Minimum 1 design idea of the site at the conceptual level. | 50% |  | To add massing to context model |  | Adequate
Example organization B
| HOOK | One sentence description of the development project, using simple language. "How you explain this to someone | Complete |  |  |  | Strong | Update: Building capacity within community, for review.
| PROJECT CHARTER | Formal document which defined the scope, deliverables and goal of the project. | 95% |  | Adjusted based on more feedback |  | adequate
| PROGRAM LIST | Listing the elements which are going to be in the new project | Complete |  |  |  | Strong | Identified as program of choice.
| BUSINESS FEASIBILITY | The hypothetical business case of the project. High-level assessment revenue vs expenses. | 75% |  | To list simple Maximum zoning envelope cost and unit number (napkin sketch) |  | adequate | Understood to be about increase production capacity.
| ZONING ENVELOPE | Created zoning envelope. | Complete |  |  |  | Strong | Many sites available/acceptable.
| ZONING ENVELOPE (REFINED) | Adjusted created zoning envelope. | 75% |  | To refine layout and circulate |  | adequate | Identified program of choice. Model ready for placement on property of choice.
| CONCEPT DESIGN (INTENTION) | Minimum 1 design idea of the site at the conceptual level. | unknown |  | To look at conceptual ethos of the piece and send to organization for review |  | In progress
Example organization C
| HOOK | One sentence description of the development project, using simple language. "How you explain this to someone | 75% | Moving forward with conversations with the city | SEND NEW PDF TO MEMBERS. | CC to pick/refine hook | adequate | The goal is to do mixed housing for financial feasibility.
| PROJECT CHARTER | Formal document which defined the scope, deliverables and goal of the project. | 50% | Team requires direction from committee? |  |  | adequate
| PROGRAM LIST | Listing the elements which are going to be contained | complete |  |  |  | strong | Organization provided a list in 1-on-1 of program views they would like.
| BUSINESS FEASIBILITY | The hypothetical business case of the project. High-level assessment revenue vs expenses. | Complete | Where is the money coming from? |  |  | adequate
| ZONING ENVELOPE | Created zoning envelope. | Complete | Confirm limiting distance |  |  | strong | Massing created for the site based on code review.
| ZONING ENVELOPE (REFINED) | Adjusted created zoning envelope. | 75% |  |  |  | adequate
| CONCEPT DESIGN (INTENTION) | Minimum 1 design idea of the site at the conceptual level. | complete |  |  |  | strong
Example organization D
| HOOK | One sentence description of the development project, using simple language. "How you explain this to someone | 95% |  | RESEND THE PDF AND COMPRESS |  | strong | Hook as part of Project charter and Visioning Committee
| PROJECT CHARTER | Formal document which defined the scope, deliverables and goal of the project. | 75% |  |  |  | strong | Approved by Board
| PROGRAM LIST | Listing the elements which are going to be contained | Complete |  |  |  | strong | Exercise completed early in design, being revisited
| BUSINESS FEASIBILITY | The hypothetical business case of the project. High-level assessment revenue vs expenses. | 50% |  |  |  | adequate | Working at community engagement to work on feasibility
| ZONING ENVELOPE | Created zoning envelope. | complete: Blender Massing was created. |  |  |  | strong | Envelope massing done for the site.
| ZONING ENVELOPE (REFINED) | Adjusted created zoning envelope. | 50% |  |  |  | adequate
| CONCEPT DESIGN (INTENTION) | Minimum 1 design idea of the site at the conceptual level. | 50% |  |  |  | adequate